## Sheet1
PROJECT CHARTER	PROJECT CHARTER

	Project Title :		Class Website Devpolment				Project Manager :		Prerana Davbhat

	Project Start Date :		22/04/24				Project Sponsor :		Snehaja Sangale

	Project End Date :		15/10/24				Email :		asdf@gmail.com

Key Schedule Milestones
Milestones						Target Date			Completion Date
1. Completion of Design phase						May 7,2024
2. Deveploment phase completion						July 7,2024
3. User Testing						August 8,2024
4. Final Review and Adjustment						September 16,2024
5. Project Launch						October 27,2024

Budget Information
Budget to complete this project is $5000

Project Objectives
1. Develop a responsive and accessible website that meets the needs of students and teachers.
2. Create a home page that provides an overview of the class and easy navigation to other sections.
3. Design a syllabus page that outlines course objectives, requirements, and schedules.
4. Implement secure login portals for students and teachers to access personalized content.
5. Include additional features such as announcements, a calendar, and a contact form.

Main Project Success Criteria

1. On-Time Delivery:
2. Create a home page that provides an overview of the class and easy navigation to other sections.
3. Functionality:
4. User Satisfaction:

Project Team						Project Approval
Project Manager						Sponsor
Project Manager						Bussiness Head
Team Members						Manager