## Sheet1
PROJECT CHARTER
| Project Title : | Class Website Devpolment |  | Project Manager : | Prerana Davbhat
| Project Start Date : | 2024-04-22 |  | Project Sponsor : | Snehaja Sangale
| Project End Date : | 2024-10-15 |  | Email : | asdf@gmail.com
Key Schedule Milestones
Milestones |  |  |  | Target Date |  | Completion Date
1. Completion of Design phase |  |  |  | May 7,2024
2. Deveploment phase completion |  |  |  | July 7,2024
3. User Testing |  |  |  | August 8,2024
4. Final Review and Adjustment |  |  |  | September 16,2024
5. Project Launch |  |  |  | October 27,2024
Budget Information
Budget to complete this project is $5000
Project Objectives
1. Develop a responsive and accessible website that meets the needs of students and teachers.
2. Create a home page that provides an overview of the class and easy navigation to other sections.
3. Design a syllabus page that outlines course objectives, requirements, and schedules.
4. Implement secure login portals for students and teachers to access personalized content.
5. Include additional features such as announcements, a calendar, and a contact form.
Main Project Success Criteria
1. On-Time Delivery:
2. Create a home page that provides an overview of the class and easy navigation to other sections.
3. Functionality:
4. User Satisfaction:
Project Team |  |  | Project Approval
Project Manager |  |  |  | Sponsor
Project Manager |  |  |  | Bussiness Head
Team Members |  |  |  | Manager