## Sheet1
PROJECT CHARTER

	Project Title :		Restaurant Management System Development				Project Manager :		Shravani Adhav

	Project Start Date :		04/22/24				Project Sponsor :		Reva Ukirde

	Project End Date :		10/15/24				Email :		asdf@gmail.com

Key Schedule Milestones
Milestones					Target Date			Completion Date
1. Completion of Design phase					May 7,2024
2. Deveploment phase completion					July 7,2024
3. User Testing					August 8,2024
4. Final Review and Adjustment					September 16,2024
5. Project Launch					October 27,2024

Budget Information
Budget to complete this project is $5000

Project Objectives
1. Develop a responsive and accessible website that meets the needs of students and teachers.
2. Create a home page that provides an overview of the class and easy navigation to other sections.
3. Design a syllabus page that outlines course objectives, requirements, and schedules.
4. Implement secure login portals for students and teachers to access personalized content.
5. Include additional features such as announcements, a calendar, and a contact form.

Main Project Success Criteria

1. On-Time Delivery:
2. Create a home page that provides an overview of the class and easy navigation to other sections.
3. Functionality:
4. User Satisfaction:

Project Team					Project Approval
Project Manager					Sponsor
Project Manager					Bussiness Head
Team Members					Manager